## Event_Log
Process Name:
Accountable Owner (A):
Version:
Date:
Next Review:
Timezone:
unit_id | stage_name | entered_at | started_at | finished_at | owner | first_pass | rework_count | wait_reason_code | notes

## Reason_Codes
code | label | definition | examples
MI | Missing/Incomplete Input | Required info/files not present at handoff; work cannot start. | Missing PO, unsigned form, absent mandatory field.
AL | Approval Lag | Waiting for a required decision/sign-off. | Manager approval pending; legal review.
AD | Access Delay | Permissions, credentials, or environment setup missing. | No system access; SSO group not provisioned.
TD | Tool Down / Integration Fail | System outage or failed sync blocks progress. | API down; import job failed.
DQ | Data Quality / Format Error | Input present but invalid or in wrong format. | Bad phone format; corrupt file.
CP | Capacity / Over WIP | Stage overloaded; queue exceeds WIP cap. | 12 items queued; team at capacity.
SC | Scope Change | Requirements changed mid-flow; rework required. | New fields requested; priority shift.
CD | Customer Delay | Waiting on external party to respond or deliver. | Client hasn’t replied; assets not received.
OT | Other (specify) | Rare, doesn’t fit above. Add brief note; review monthly to refine codes. | Unique regulator request.